## 1. Product Overview
Item | Description
Product Name | CAMP — Course Alignment & Mapping Portal
Product Vision / Purpose | To eliminate the manual, time-intensive BOS documentation burden on faculty in Indian engineering colleges by auto-generating BOS-ready deliverables — CO-PO matrix, Bloom's taxonomy table, unit-wise syllabus, and textbook validation — reducing a 7–20 day manual process to under 30 minutes.
Business Goals / Key Success Factors | 1. Reduce course documentation time by 90% 2. Ensure AICTE compliance across affiliated Karnataka colleges 3. Achieve adoption in 3+ universities in Year 1 4. Generate revenue via Premium BOS Review Dashboard 5. Attain 4.5+ satisfaction rating from faculty users
Primary Stakeholders | Faculty Members · Heads of Departments (HODs) · Board of Studies (BOS) · Students · Institution / College Management · AICTE

## 2. Product Backlog
Epic ID | Epic Title | User Story ID | User Story / Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
E1 | User Authentication | US1 | As a faculty, I want to register with my email and OTP so I can securely access CAMP. | Registration screen, OTP generation, Email sending, Pop-up on success | Must Have | 8 | To Do | Backend Team | Registration & OTP flow test cases | QA Lead
|  | US2 | As a faculty, I want to log in with email and OTP so I can access my saved courses. | Login screen, OTP validation, Error screens, Session management | Must Have | 5 | To Do | Backend Team | Login & session test cases | QA Lead
|  | US3 | As a faculty, I want to reset my account access if I lose my OTP. | Forgot/resend OTP flow | Should Have | 3 | To Do | Backend Team | OTP resend test cases | QA Lead
E2 | Dashboard | US4 | As a faculty, I want to see my saved courses on a dashboard so I can manage them easily. | Dashboard UI, Course cards, Status badges, Search & filter | Must Have | 8 | In Progress | Frontend Team | Dashboard render & filter tests | QA Lead
|  | US5 | As a faculty, I want to view analytics (Bloom's distribution, CO-PO heatmap) on my dashboard. | Analytics widgets, Chart.js integration, CO-PO heatmap | Should Have | 13 | In Progress | Frontend Team | Analytics display tests | QA Lead
E3 | Mode B — New Course Creation | US6 | As a faculty, I want to enter a course title and COs so CAMP auto-generates the full syllabus. | CO input wizard (3 steps), Syllabus generation engine, Unit-wise output | Must Have | 13 | In Progress | Full Stack Team | Syllabus generation accuracy tests | QA Lead
|  | US7 | As a faculty, I want CAMP to auto-classify my COs using Bloom's Taxonomy. | Bloom's verb detection algorithm, Taxonomy table rendering | Must Have | 8 | In Progress | Backend Team | Bloom's classification accuracy | QA Lead
|  | US8 | As a faculty, I want CAMP to auto-generate a CO-PO matrix from my course outcomes. | CO-PO mapping engine, Matrix rendering, Correlation scoring (1/2/3) | Must Have | 13 | To Do | Backend Team | CO-PO mapping accuracy tests | QA Lead
E4 | Mode A — Course Updation | US9 | As a faculty, I want to paste my existing syllabus so CAMP can show what changed. | Existing syllabus input, Diff engine (added/removed/modified topics), Modification % stats | Must Have | 13 | To Do | Full Stack Team | Diff engine test cases | QA Lead
|  | US10 | As a faculty, I want a side-by-side comparison of old vs new course content. | Comparison panel, Colour-coded changes (green=added, red=removed) | Should Have | 8 | To Do | Frontend Team | Visual diff test cases | QA Lead
E5 | Textbook Validator | US11 | As a faculty, I want CAMP to flag outdated textbooks (>8 years old) so my BOS submission is credible. | Textbook year input, Age validator, Warning tooltip on old books | Should Have | 5 | To Do | Frontend Team | Textbook validator test cases | QA Lead
E6 | BOS Review Dashboard (Premium) | US12 | As a BOS member, I want a 3-way comparison (old vs new vs reference university course) to review submissions faster. | 3-panel comparison view, Reference doc upload, Highlight diff view, Summary stats | Could Have | 20 | To Do | Full Stack Team | BOS dashboard comparison tests | QA Lead
|  | US13 | As a BOS member, I want to export the comparison report as a PDF. | PDF export of BOS comparison panel | Could Have | 8 | To Do | Backend Team | PDF export test cases | QA Lead
E7 | Export & Output | US14 | As a faculty, I want to export my complete BOS-ready document package as a .docx file. | docx.js integration, CO-PO matrix export, Bloom's table, Syllabus, Textbooks in Word format | Must Have | 13 | To Do | Full Stack Team | Export format & content tests | QA Lead
Notes:
|  | Must Have | Critical — essential for project success; must be delivered.
|  | Should Have | Important but not vital; project can launch without, but less ideal.
|  | Could Have | "Nice-to-have" — lower impact if excluded.
|  | Won't Have | Out of current scope; considered for future iterations.

## 3. Roadmap
Release | Target Date | Key Features / Epics | Dependencies | Demo Status
v0.1 | Apr 19, 2026 | E1: User Authentication (Registration, OTP Login, Session) | — | Planned
v0.2 | Apr 26, 2026 | E2: Dashboard UI, Course cards, Search & filter | Requires v0.1 Auth | Planned
v0.3 | May 3, 2026 | E3: Mode B — New Course Wizard (CO input, Bloom's, Syllabus gen) | — | Planned
v0.4 | May 10, 2026 | E3 cont. — CO-PO Matrix engine + Matrix rendering | Requires Bloom's engine | Planned
v0.5 | May 17, 2026 | E4: Mode A — Course Updation + Diff engine | Requires Mode B base | Yet to Plan
v0.6 | May 24, 2026 | E5: Textbook Validator + E7: .docx Export | Requires complete course output | Yet to Plan
v1.0 | May 31, 2026 | Full Integration: Auth + Dashboard + Mode A & B + Export | All prior releases | Yet to Plan
v1.1 | Jun 7, 2026 | E6: BOS Review Dashboard (Premium) — 3-way comparison + PDF export | Requires v1.0 | Yet to Plan

## 4. Retrospective
Note: Retrospective to be completed at the end of each release sprint. Be honest — this is for the team to learn and grow.
What Went Well | What Didn't Go Well | Improvements / Action Items | Owner
Frontend prototype was completed and working end-to-end | CO-PO mapping accuracy needs improvement | Invest time in refining the keyword-to-PO scoring algorithm before v0.4 | Backend Team